## 0. Overview
Annexure A
PROCUREMENT PROCESS BOOK
DIGITAL EQUIPMENT MANAGEMENT SYSTEM- End-to-End Process Documentation
TABLE OF CONTENTS
Sheet Name | Process Area | Description
0. Overview | Cover/TOC | Version history, table of contents, glossary
1. Indent Receipt | Indent Processing | DEO at HoD enters indent → TGMSIDC User reviews/verifies vs scanned copy & corrects → forwards to SO Equipment for approval
2. Indent Approval | Indent Processing | SO reviews, approves/returns/rejects indent; selects procurement mode
3. RC Creation | Rate Contract Mgmt | Create new rate contracts when no existing RC covers the equipment
4. RC Management | Rate Contract Mgmt | Monitor expiry, amend, renew, or close existing rate contracts
5. Issue PO | Purchase Order Mgmt | Generate PO from approved indent linked to active RC
6. PO Approval | Purchase Order Mgmt | Approve, modify, or reject draft POs
7. PO Amendment & Cancellation | Purchase Order Mgmt | Amend quantities/dates/consignees or cancel POs with audit trail
8. Delivery & Receipt | Delivery & Acceptance | Track shipments, record receipt at consignee, log discrepancies
9. QA & Acceptance | Delivery & Acceptance | Inspect, test, accept/reject equipment; trigger warranty & payment
10. Workflow Summary | Workflow Integration | Status transitions, SLA targets, parallel processing rules
11. Master Data | Supporting Config | Equipment, Institution, Vendor, Account Head, Programme, Tax masters
12. Functionalities | System Requirements | Feature list with business rules, validations, priorities, and use cases
13. Reports & Dashboards | Reporting & Analytics | 15 report definitions + 12 KPI specifications
GLOSSARY
Abbreviation | Full Form
TGMSIDC | Telangana Medical Services & Infrastructure Development Corporation
MD | Managiging Director, TGMSIDC
ED | Executive Director, TGMSIDC
SO Equip | Special Officer Equipment, TGMSIDC
GM Equip | General Manager – Equipment, TGMSIDC
HOD | Head of Department
RC | Rate Contract
PO | Purchase Order
FY | Financial Year
GO | Government Order
PS | Performance Security
CAMC | Comprehensive Annual Maintenance Contract
QA | Quality Assurance
LD | Liquidated damages
L1/L2/L3 | nm
SLA | Service Level Agreement
GST/IGST/CGST/SGST | Goods & Services Tax / Integrated / Central / State GST
HSN | Harmonised System of Nomenclature (tax classification code)
DEO | Data Entry Operator – staff at HoD facility who enters indent details into the tool on behalf of the HoD
BFC | Bill Finalisation Committee – approves financial bids and procurement decisions
e-Procurement | Government of Telangana's electronic procurement portal for tender management

## 1. Indent Receipt
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | DEO logs into the tool | Data Entry Operator (DEO) at the HoD facility logs into the procurement tool using HoD-specific login credentials. DEO navigates to 'Create New Indent'. Process moves to Step 2. | – Role-based access: DEO can only create/edit indents for their own HoD. – Dashboard shows DEO's draft indents and submitted indent status. – Session timeout after 30 min inactivity. | HoD login credentials | Indent creation screen | E-tool | DEO (HoD) | DEO (HoD) | HoD | — | No | If DEO has login issues, contact TGMSIDC Admin. Each HoD gets one or more DEO logins.
2 | Enter indent header details | DEO enters indent header and uploads scanned copy of physical indent: 1. HoD name (auto-filled from login; read-only) 2. Indent type (Letter / GO / Proceeding) 3. Indent reference no. 4. Financial year 5. Indent date 6. Funding source (from master) 7. Programme name (from master) 8. Account head (from master) Upload scanned copy of original indent (mandatory). Process moves to Step 3. | – HoD name auto-populated from DEO's login profile (not editable by DEO). – System logs receipt timestamp. – Auto-generates unique Indent Tracking ID. – Indent ref. no. must be unique (duplicate check). – Mandatory-field validation on save. – Auto-populate programme, funding source & account head from masters. – Scanned copy upload mandatory (PDF/JPG/PNG, max 30 MB). | Physical indent document; Master lists | Indent Tracking ID; Draft indent record | E-tool | DEO (HoD) | DEO (HoD) | HoD | TGMSIDC | No | If data missing on physical indent, DEO should coordinate with HoD before entering.
3 | Add institutions for which indent is raised | Select institutions from Institution Master. Institution is linked to district automatically. Process moves to Step 4. | – Validate institution exists in master. – Auto-populate district from institution master. – Allow multi-select. – DEO can only see institutions under their HoD's jurisdiction (filtered view). | Institution Master | Institutions linked to indent | E-tool | DEO (HoD) | DEO (HoD) | HoD | TGMSIDC | No
4 | Enter equipment details | Select equipment from the Equipment Master list. For each line: • Department • Equipment name & category (Only equipment linked to that department and type of health facility will be displayed) • Specifications (long-text) (Auto filled) If the equipment is NOT found in the master list: • DEO selects 'Equipment not in list' option • Manually types: Equipment name + Specifications (free-text) • This entry is flagged as 'Unverified – Pending Master Mapping' Process moves to Step 5. | – Auto-suggest from Equipment Master as DEO types. – If selected from master → spec template pre-filled. – If 'Equipment not in list' selected → free-text fields enabled for name + specs. – Free-text entries flagged with 'Unverified' badge. – Validate at least one equipment line exists. – System logs whether each line is 'From Master' or 'Write-in'. | Equipment Master | Equipment line items (master-matched or write-in) | E-tool | DEO (HoD) | DEO (HoD) | Concerned health facility | TGMSIDC | No | Write-in entries will be resolved by TGMSIDC User in Step 12 (review stage).
5 | Map equipment quantities per institution | For each institution, fill: 1. Sanctioned quantity Process moves to Step 6. | – Validate: Total qty per equipment across all institutions = indent total. – Auto-sum quantities. | Indent details | Equipment-institution quantity matrix | E-tool | DEO (HoD) | DEO (HoD) | HoD | TGMSIDC | No
6 | Enter fund details for each institute | Enter: 1. Fund sanctioned(AS) amount 2. Fund sanction date 3. Fund deposited amount (if applicable) 4. Cheque / UTR no. (if applicable) 5. Fund deposit date (if applicable) Process moves to Step 7. | – Date validations (deposit date ≤ today). – Fund deposited ≤ Fund sanctioned (if both entered). | Fund sanction documents | Fund details linked to indent | E-tool | DEO (HoD) | DEO (HoD) | HoD | TGMSIDC | No
7 | Validate indent completeness | System runs completeness check across all mandatory fields before allowing submission. If validation passes → Process moves to Step 8 (save draft) or Step 9 (submit). If validation fails → DEO must correct errors and re-validate. | – Mandatory-field check. – Highlight any empty mandatory cells in red. – Flag if any equipment line is 'Write-in' (warning, not a blocker). – Summary of validation results shown to DEO. | All prior data entries | Validation pass / fail report | E-tool | DEO (HoD) | DEO (HoD) | HoD | — | Yes | If validation fails → DEO must correct errors before proceeding.
8 | Save as draft (optional) | Save current indent as draft for later completion. Process moves to Step 9 when DEO is ready to submit. | – Status = 'Draft'. – Visible in DEO's draft queue. – Drafts auto-flagged after 30 days of inactivity (configurable). – TGMSIDC User cannot see drafts; only submitted indents. | Draft indent data | Saved draft | E-tool | DEO (HoD) | DEO (HoD) | HoD | — | No
9 | Submit indent to TGMSIDC for review | DEO submits the completed indent. The indent goes to TGMSIDC User's review queue Process moves to Step 10. | – Status changes: Draft → 'Pending TGMSIDC Review'. – Notification (email + in-app) sent to TGMSIDC User. – Submission timestamp recorded. – Indent locked from DEO editing after submission. – DEO can track indent status on their dashboard. | Validated indent | Indent in TGMSIDC review queue; notification to TGMSIDC User | E-tool | DEO (HoD) | DEO (HoD) | HoD | TGMSIDC User | No | Once submitted, DEO cannot edit unless returned by TGMSIDC User.
10 | TGMSIDC User reviews indent against scanned copy | TGMSIDC User opens the indent from the review queue. Verifies all DEO-entered data against the uploaded scanned copy: 1. HoD name & indent reference 2. Equipment names, specs & quantities 3. Institutions & quantity mapping 4. Fund details 5. Completeness and accuracy TGMSIDC User can view the scanned copy for each institute side-by-side with entered data. Process moves to Step 11. | – Side-by-side view: entered data (left) vs. scanned copy (right). – Discrepancies between data and scan highlighted. – 'Write-in' equipment flags shown prominently. – Aging indicator: Green <2d, Amber 2-3d, Red >3d. | Submitted indent; Scanned copy | Review findings | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | DEO (HoD) | No
11 | TGMSIDC User edits / corrects indent data (if needed) | TGMSIDC User can directly edit fields to correct errors: • Fix quantities, dates, fund details • Add missing information All edits tracked: system logs DEO's original value vs. TGMSIDC User's corrected value. If write-in equipment entries exist → Process moves to Step 12. If no write-ins → Process moves to Step 13. | – Edit audit trail: for each corrected field, system stores: • Original value (entered by DEO) • Corrected value (entered by TGMSIDC User) • Timestamp of correction • User who made the correction – Correction count per indent tracked for DEO quality reporting. – Edited fields visually marked (blue highlight) to distinguish from original entries. | Indent data; Scanned copy | Corrected indent data; Edit audit log | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | DEO (HoD) | No | DEO is not notified of corrections but can view edit history on their dashboard.
12 | Resolve write-in equipment entries (if any) | For each equipment line flagged as 'Write-in', TGMSIDC User must resolve: Option A – Map to existing master item: • Search Equipment Master and link the write-in to an existing entry • (DEO may have used a different name for equipment already in master) Option B – Flag as new equipment addition request: • Confirm equipment is genuinely not in master • Raise 'New Equipment Addition Request' to GM Equipment • Indent can proceed with write-in entry (flagged) pending master update Process moves to Step 13. | – Write-in entries highlighted with 'Unverified' badge. – TGMSIDC User must resolve each write-in before forwarding (mandatory). – Option A: Line updated to reference master entry; original write-in text preserved in notes. – Option B: 'New Equipment Addition Request' auto-created → routed to GM. – Once GM approves new equipment, master updated for future indents. – Resolution status: 'Mapped to Master' or 'New Addition Requested'. | Write-in equipment entries; Equipment Master | Resolved equipment lines; New addition requests (if any) | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | DEO (HoD) | Yes | This step is skipped if all equipment lines were selected from master (no write-ins).
13 | Decision: Forward to GM or Return to DEO | After review, correction, and write-in resolution: • Satisfied (if no changes from the indent raised by DEO) → Forward indent to GM Equipment for approval. Process moves to Step 14. • Issues needing DEO input → Return to DEO with comments. Process moves back to Step 9 after DEO corrections. | – If forwarded: Status → 'Pending Approval' (GM queue). – If returned: Status → 'Returned by TGMSIDC'. DEO notified with comments. – Return requires mandatory comments explaining what DEO needs to fix. – DEO can re-edit and re-submit. – Forwarding timestamp recorded. | Reviewed indent; Decision | Indent in GM queue OR returned to DEO | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | DEO (HoD) / HoD | Yes | If returned, cycle repeats from Step 9 after DEO corrections.
14 | Forward indent for GM Equipment approval | TGMSIDC User forwards the verified indent to GM Equipment. Process moves to → Sheet 2. Indent Approval (Step 1). | – Status: 'Pending Approval'. – Notification (email + in-app) sent to GM Equipment. – Indent locked from TGMSIDC User editing. – GM can see: DEO original entries, TGMSIDC corrections (if any), write-in resolutions, scanned copy. | Verified & corrected indent | Indent in GM approval queue; notification to GM | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | DEO (HoD) / HoD | No

## 2. Indent Approval
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Open pending-indent approval queue | GM Equipment opens approval queue. Filter by: 1. HoD type 2. Indent type / Order type 3. Financial year 4. Date range Process moves to Step 2. | – Dashboard tile: count of pending indents. – Aging indicator: Green <7d, Amber 7-14d, Red >14d. – Sort by oldest-first (default). – GM can see TGMSIDC review status and correction count for each indent. | Pending indent list | Filtered indent list on screen | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
2 | Select indent reference number | Click on an indent reference number to open its full details. Process moves to Step 3. | – Display: header, equipment list, institution-qty matrix, fund details, scanned copy. – Show DEO original entries vs. TGMSIDC corrections (edit audit trail). – Write-in resolution status visible. – Read-only view. | Indent ref. no. | Full indent detail screen | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
3 | Verify indent details | For each equipment / institution line, verify: 1. Equipment specification 2. Requested qty vs. sanctioned qty 3. Budget adequacy (estimated cost vs. fund available) 4. No duplication with existing indents/POs Process moves to Step 4. | – System highlights discrepancies (qty mismatch, budget shortfall). – Show existing active RC coverage for the equipment. – Show any 'New Equipment Addition Requests' flagged by TGMSIDC User. | Indent data; Historical records | RC Status; Verification notes | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
4 | Enter approved quantity per equipment line | For each equipment line, enter the quantity to be approved (may be ≤ requested quantity). Process moves to Step 5. | – Validate: Approved qty ≤ Requested qty. – Auto-recalculate estimated cost based on approved qty. – If partial approval → mandatory reason/comment. | Indent data | Approved quantity per line | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No | Partial approvals must carry forward reasoning to PO stage.
5 | Select procurement mode per equipment | For each equipment line, select mode: i) Rate Contract (RC) – if a valid RC exists ii) Open / Limited Tender – if no RC exists iii) Local Purchase – for low-value items under threshold Process moves to Step 6. | – System auto-checks RC availability for each equipment. – If active RC found → pre-select 'RC' and display RC details. – If no active RC → highlight and recommend 'Tender'. | RC Master; Equipment data | Procurement mode per equipment line | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | Yes | Procurement mode drives downstream routing (RC → PO; Tender → RC Creation first).
6 | Approve / Return / Reject indent | Update the status as Proposed to Approve Proposed to Return to TGMSIDC user (along with reason) Proposed to Reject (along with reason) The process moves to Step 7 | – Mandatory comments for Return / Reject. – GM can view: DEO original entries, TGMSIDC corrections, scanned copy. | Verified indent; Decision | Status update; Notifications; Audit log | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | TGMSIDC GM Equip | No
7 | Review by SO Equipment | Decision taken in step 6 will be reviewed by SO equipment. Approve → Process moves to Step 8 (auto-routing). Return → sent back to TGMSIDC User (who may return to DEO if facility input needed). Process moves back to "Indent receipt", Step 10. Reject → indent closed with documented reason. Process ends.) | SO Equipment reviews the action taken by GM Equipment. – Status updated: 'Approved' / 'Returned' / 'Rejected'. – Notification to TGMSIDC User, GM Equipment, DEO (HoD) & HoD. – Audit log entry with decision, timestamp, comments. – Mandatory comments for Return / Reject. – SO Equipment can view: DEO original entries, TGMSIDC user corrections, scanned copy. |  | Status update; Notifications; Audit log | E-tool | TGMSIDC SO Equip | TGMSIDC SO Equip | TGMSIDC GM Equip | DEO (HoD) / HoD | Yes
8 | Route based on procurement mode | If approved, system auto-routes each equipment line: • RC mode → "Issue PO" (Step 1) • Tender mode → "RC Creation" (Step 1) Process moves to the respective sheet based on procurement mode selected above. | – Create workflow tasks in respective queues. – Parallel routing: different equipment items from same indent can follow different paths simultaneously. – Status per equipment line visible on indent dashboard. | Approved indent with modes | Workflow tasks created in target queues | E-tool | System (auto) | TGMSIDC SO Equip | TGMSIDC GM Equip | DEO (HoD) / HoD/GM Equipment, TGMSIDC User | No | Indent-level status = 'Partially Approved' if some lines go to tender, some to RC.

## 3. RC Creation
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Initiate new RC process | TGMSIDC User navigates to Rate Contract module and clicks 'Add New RC'. Enter: 1. Equipment name – select from Equipment Master or enter write-in name (from indent) 2. Equipment category / department 3. Linked indent reference (if applicable) Process moves to Step 2. | – Auto-generate draft RC ID: RC-<FY>-<serial>. – Duplicate check: block if active RC already exists for same equipment. – If equipment selected from master → flag as 'Existing Equipment'. – If equipment is a write-in (not in master) → flag as 'New Equipment'. – Equipment flag drives Step 2 behaviour. | Equipment Master; Indent reference | Draft RC ID; Equipment linked to RC process | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | TGMSIDC SO Equipment | No
2 | Check technical specifications availability | System checks whether the equipment is existing (specs available in master) or new (no specs available). → If Existing Equipment (specs available): Process moves to Step 3. → If New Equipment (no specs): Process moves to Step 4. | – Existing equipment: Pre-load technical specifications from Equipment Master. – New equipment: Show empty specification form. – Display equipment flag: 'Existing – Specs Available' or 'New – Specs Required'. | Equipment Master | Specification status determined | E-tool | System (auto) | TGMSIDC User | — | — | Yes
3 | Confirm / revise specifications (Existing Equipment) | For existing equipment, technical specifications are pre-loaded from master. TGMSIDC User presents specs to doctors in Specifications committee assigned by the respective HoD who raised the indent. Doctors review and decide: Option A – 'Specifications Accepted' (no changes): • Upload signed specification document (PDF/scan) • Enter doctor/approver names (who confirmed) • Date and time auto-filled by system Option B – 'Specifications Changed': • Upload signed document with revised specifications • Enter doctor/approver names (who approved changes) • Date and time auto-filled by system • Revised specs saved to the RC record Process moves to Step 5. | – Two radio buttons: 'Accepted' / 'Changed'. – Upload field: Signed specification document (mandatory, PDF/JPG/PNG, max 30 MB). – Text fields: Doctor/approver names (mandatory, comma-separated or multi-entry). – Date & time: Auto-populated (read-only, system timestamp). – If 'Changed': Additional text area for revised specifications (mandatory). – If 'Changed': Revised specs stored as new version; original preserved in history. – Specification confirmation status logged for audit. | Pre-loaded specs from master; Doctor review | Confirmed/revised specs; Signed document; Approver names | E-tool | TGMSIDC User | TGMSIDC User | Doctors (HoD-assigned) | TGMSIDC GM Equip / HoD | No | Doctors are assigned by the HoD who raised the indent. Their names must be recorded.
4 | Add new specifications (New Equipment) | For new equipment (not in master), no specifications exist. TGMSIDC User: 1. Enter new technical specifications as per the recommendation by HoD in the specification form 2. Get confirmation from doctors assigned by the respective HoD 3. Upload signed specification document with the new specs 4. Enter doctor/approver names (who confirmed the new specs) 5. Date and time auto-filled by system Process moves to Step 5. | – Specification form: Free-text fields for new equipment specs. – Upload field: Signed specification document (mandatory). – Text fields: Doctor/approver names (mandatory). – Date & time: Auto-populated (read-only). – New specs stored as the initial version for this equipment. – Flag: 'New Equipment – Specs Pending Master Addition'. | Doctor consultation; New equipment requirements | New specifications; Signed document; Approver names | E-tool | TGMSIDC User | TGMSIDC User | Doctors (HoD-assigned) | TGMSIDC GM Equip / HoD | No | New equipment specs will be added to Equipment Master after RC is approved (master data update request).
5 | Technical specifications finalized | Specifications are now finalized (either confirmed, revised, or newly created). TGMSIDC User proceeds to enter the tender on the e-Procurement / GeM portal. Process moves to Step 6. | – Status: 'Specs Finalized'. – Specification document linked to RC record. – Audit trail: Spec version, confirmation type (Accepted/Changed/New), approver names, timestamp. – Specs locked from further editing unless a new tender cycle is initiated. | Finalized specifications | Specs locked; Ready for tendering | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | SO-TGMSIDC | No
6 | Enter tender on e-Procurement / GeM portal | TGMSIDC User creates the tender on the external e-Procurement portal or GeM portal In our tool, enter: 1. Tender reference number (from e-Procurement / GeM) 2. Tender date 3. Tender type (Open / Limited) 4. Portal used (e-Procurement / GeM) 5. Link equipment to this tender reference Process moves to Step 7. | – Tender ref. no. must be unique in our system. – Link tender to the RC draft and equipment. – If this is a re-tender (after cancellation), link to previous cancelled tender. – Tender audit trail entry created: Equipment Name ¦ Tender Ref No ¦ Tender Date ¦ Status = 'Active'. | Finalized specs; e-Procurement/GeM portal | Tender record created in our tool; Linked to RC | E-tool + e-Procurement/GeM | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | SO-TGMSIDC | No | Actual tender creation happens on external portal. Our tool tracks the reference and stages.
7 | Stage: Tender Opened | Record that the tender has been activated and opened on the e-Procurement / GeM portal. Enter: 1. Tender opening date 2. Bid submission start date 3. Bid submission end date 4. Remarks (if any) Process moves to Step 8. Note: At this stage or any subsequent stage (Steps 7–15), if the tender is cancelled, Process moves to Step 16 (Tender Cancellation). | – Status: 'Tender Opened'. – Timeline tracking begins. – Tender stage progress bar updated in dashboard. | Tender activation on external portal | Tender opening record; Dates captured | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendors | No | From this step onwards, tender can be cancelled at any stage → Step 17.
8 | Stage: Pre-bid Queries | Record pre-bid queries stage: 1. Were pre-bid queries received? (Yes / No) 2. If Yes: Upload pre-bid queries document 3. Upload pre-bid responses document (if applicable) 4. Pre-bid meeting date (if held) Process moves to Step 9. | – Optional stage: If no queries received, mark as 'No Queries' and proceed. – Upload fields for queries and responses documents. – Pre-bid meeting date (optional). – Status: 'Pre-bid Queries Stage'. | Vendor queries from portal | Pre-bid queries record; Response documents | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendors | No
9 | Stage: Amendments (if any) | Record any amendments made to the tender document: 1. Were amendments made? (Yes / No) 2. If Yes: Upload amended tender document 3. Amendment description / summary 4. Amendment date Process moves to Step 10. | – Optional stage: If no amendments, mark as 'No Amendments' and proceed. – Upload field for amended document. – Amendment summary text field. – Status: 'Amendments Stage'. | Pre-bid feedback; Internal review | Amendment record (if any) | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendors | No
10 | Stage: Bid Evaluation | All received bids are downloaded from the e-Procurement / GeM platform. Bid evaluation process begins according to prescribed criteria. Record: 1. Number of bids evaluated 2. Bid evaluation start date 3. Bid evaluation completion date 4. Upload bid evaluation report (if available at this stage) Process moves to Step 11. | – Status: 'Bid Evaluation Stage'. – Numeric fields for bid count. – Date fields for evaluation period. – Upload field for evaluation report. | Bids from portal | Bid evaluation record | E-tool + e-Procurement/GeM | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | SO-TGMSIDC | No
11 | Stage: Demo & Technical Evaluation | Technical committee examines and verifies samples / demos provided by vendors against the technical specifications. Record: 1. Demo date(s) 2. Technical evaluation date(s) 3. Names of technical committee members 4. Upload technical evaluation report Process moves to Step 12. | – Status: 'Demo & Technical Evaluation Stage'. – Date fields. – Committee member names (text field). – Upload field for evaluation report. – Link to finalized specifications for comparison. | Vendor samples/demos; Finalized specs | Technical evaluation record; Report uploaded | E-tool + Physical | TGMSIDC User | TGMSIDC GM Equip | Technical Committee | Vendors | No | Technical committee composition may vary by equipment type.
12 | Stage: Approved by Technical Committee? | Decision: Is atleast vendor/equipment recommended by the Technical Committee? → If YES: Process moves to Step 13. If no vendor is qualified, Process moves to Step 16 (Tender Cancellation). TGMSIDC User enters reason. A fresh tender will be initiated from Step 6. | – Decision: 'Yes – Recommended' / 'No – Not Recommended'. – If No: Mandatory cancellation reason. – If Yes: Record names of approved/recommended vendors. – Upload signed technical committee recommendation report. | Technical evaluation report | Recommendation decision; Approved vendor list (if Yes) | E-tool | Technical Committee | TGMSIDC GM Equip | TGMSIDC User | SO-TGMSIDC / Vendors | Yes
13 | Stage: Financial Bid Opening & BFC Agenda Preparation | Financial bids of technically qualified vendors are opened. Matter is placed before the Bid Finalisation Committee (BFC) for approval. Record: 1. Financial bid opening date 2. L1, L2, L3 vendor details and quoted rates 3. BFC agenda preparation date 4. Upload financial bid comparison sheet Process moves to Step 14. | – Status: 'Financial Bid & BFC Prep Stage'. – Vendor-wise rate entry fields (L1/L2/L3). – Upload field for financial bid comparison. – BFC agenda date field. | Financial bids from portal | Financial bid record; L1/L2/L3 rates; BFC agenda | E-tool + e-Procurement/GeM | TGMSIDC User | TGMSIDC GM Equip | SO-TGMSIDC,ED-TGMSIDC | Vendors | No
14 | Stage: BFC Meeting | BFC meeting is scheduled and conducted. Record: 1. Tentative BFC date (entered in advance) 2. Actual BFC meeting date 3. BFC members present 4. Upload BFC minutes / proceedings Process moves to Step 15. | – Status: 'BFC Stage'. – Tentative date field (can be entered before meeting). – Actual date field (entered after meeting). – Text field for BFC members. – Upload field for BFC minutes. | BFC agenda; Financial bid comparison | BFC meeting record; Minutes uploaded | E-tool | TGMSIDC GM Equip | ED-TGMSIDC | BFC Members | TGMSIDC User | No
15 | Stage: BFC Approved? | Decision: Has the BFC approved the procurement? → If YES: Process moves to Step 17 (RC Header Details). → If NO: Tender cancelled at BFC stage. Process moves to Step 16 (Tender Cancellation). TGMSIDC User enters reason. A fresh tender will be initiated from Step 6. | – Decision: 'Yes – BFC Approved' / 'No – BFC Rejected'. – If No: Mandatory cancellation reason. – If Yes: BFC approval reference number / date. – Upload signed BFC approval document. | BFC proceedings | BFC decision; Approval document (if Yes) | E-tool | BFC | ED-TGMSIDC | TGMSIDC GM Equip | TGMSIDC User / Vendors | Yes
16 | Tender Cancellation (at any stage) | If the tender is cancelled at any stage (Steps 7–15), TGMSIDC User must: 1. Select the stage at which cancellation occurred 2. Enter detailed reason for cancellation (mandatory) 3. Upload supporting document (if any) 4. Confirm cancellation Tender status → 'Cancelled'. Tender audit trail updated: Status = 'Cancelled', Stage of cancellation, Reason. To initiate a fresh tender → Process moves back to Step 6 (new tender reference number will be entered). The cancelled tender record is preserved for audit. | – Tender status: 'Cancelled'. – Mandatory fields: Stage of cancellation (dropdown from Steps 7–16), Reason (text). – Optional: Upload supporting document. – Cancelled tender remains in audit trail (never deleted). – New tender initiated gets linked to cancelled tender as 'Re-tender'. – Tender audit report updated automatically. – Notification to GM and ED about cancellation. | Cancellation decision; Reason | Cancelled tender record; Audit trail updated | E-tool | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | HoD | No | Multiple re-tenders for same equipment are tracked in Tender Audit Report.
17 | Enter RC header details | Post BFC approval, enter RC header 1. RC reference number (unique: Auto Populated) 2. L1 / L2 / L3 vendor tier 3. Award date 4. Contract start date (From) 5. Contract end date (To) 6. Supply & installation period (days) Process moves to Step 18. | – RC ref. no. duplicate check → block if exists. – Validate: End date > Start date. – Auto-calculate RC validity period in months. – Alert if validity > 24 months (unusual). – Link to BFC approval document and tender reference. | BFC approval; Tender evaluation outcome | RC header record | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No
18 | Enter tender reference & bank details | Enter: 1. Financial year 2. Tender reference no. (already linked from Step 6; verify) 3. Bank details for each vendor: name, branch, IFSC, account no. System auto-populates from Tender Ref. No.: • Tender bid date, Price bid date, Tender detail • Supplier details – L1, L2, L3 (name, email, phone, address) • Equipment: name, model, installation type, training required, specifications • Contract copy (attachment) Process moves to Step 19. | – Auto-fetch tender data from tender reference. – Validate IFSC format (11-char alphanumeric), bank account no. length. – If tender ref. not found → allow manual entry with mandatory document upload. – Highlight auto-populated fields for user review. | Tender reference no.; Bank details | Tender & supplier details populated | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No | If tender data not in system, user must upload complete tender evaluation report.
19 | Enter rate / pricing details | Enter per vendor (L1/L2/L3): 1. Rate per unit (excl. tax) 2. Tax type (GST) 3. IGST % or (CGST% + SGST%) 4. Rate per unit incl. tax (auto-calculated) 5. Warranty period (months) 6. Max order quantity (if applicable) Process moves to Step 20. | – Auto-calculate: Tax amt = Rate × Tax%. – Auto-calculate: Rate incl. tax = Rate + Tax amt. – Validate tax% against GST slab master. – Store rate history for audit. – Rates should match BFC-approved rates. | BFC-approved rates; Tender price bid | Pricing details per vendor | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No
20 | Enter CAMC details | Enter: 1. CAMC applicable? (Yes / No) 2. CAMC period (years) 3. CAMC rate per year 4. CAMC start date (auto = warranty end + 1 day) 5. CAMC terms & conditions Process moves to Step 21. | – Auto-calculate CAMC start date from warranty end. – Validate CAMC period ≤ configurable max. – CAMC details optional if CAMC = No. | Warranty period; CAMC terms | CAMC details linked to RC | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No | CAMC terms to be confirmed with vendor before finalization.
21 | Upload supporting documents | Upload: 1. Signed contract copy (mandatory) 2. Tender evaluation report 3. BFC approval document 4. Technical committee recommendation 5. Specification confirmation document (from Step 3/4) 6. Any other supporting document Process moves to Step 22. | – File type validation: PDF, JPG, PNG only. – Max file size: 30 MB per file. – At least contract copy + BFC approval are mandatory. – All documents linked to RC record. | Physical / scanned documents | Documents attached to RC record | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No
22 | Submit RC for approval | Submit the completed RC for GM Equipment / ED review. Process moves to Step 23. | – Status: 'Pending RC Approval'. – Notification to approver (GM / ED). – RC locked from editing. – Submission timestamp logged. – Full audit trail visible: specs → tender stages → BFC → RC details. | Complete RC draft | RC in approval queue; notification | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No
23 | Proposed to Approve / Return / Reject RC | GM reviews all RC details including tender history, BFC approval, and specs confirmation: • Proposed to Approve • Proposed to Return • Proposed to Reject. | – Status updated & sent to SO Equipment for review | RC draft; Reviewer's assessment | Proposed to Active RC / Returned RC / Rejected RC | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | SO-TGMSIDC | No | Approval authority based on RC value threshold (configurable).
24 | Approve / Return / Reject RC | SO Equipment reviews all RC details including tender history, BFC approval, and specs confirmation: • Approve → RC status = 'Active'; available for PO linking. Process moves to → Sheet 5. Issue PO when indent requires PO. • Return → sent back for corrections with comments. Process moves back to Step 18. • Reject → RC closed. Process ends. If equipment was 'New' (from Step 4), upon RC approval, system auto-raises 'New Equipment Addition Request' to update Equipment Master. | – Status updated. – If Approved: RC visible in RC master for PO generation. – Notification to TGMSIDC User, relevant vendors. – Audit log with decision + comments. – Mandatory comments for Return / Reject. – If new equipment: trigger Equipment Master addition workflow. | RC draft; Reviewer's assessment | Proposed to Active RC / Returned RC / Rejected RC | E-tool | SO-TGMSIDC | TGMSIDC GM Equip | TGMSIDC GM Equip | Vendors, ED | Yes | Approval authority based on RC value threshold (configurable).

## 4. RC Management
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Monitor RC dashboard | View consolidated RC dashboard: • Active RCs with remaining validity • RCs expiring in 30 / 60 / 90 days • Expired RCs • RCs by equipment category / vendor Process moves to Step 2 (if alert received) or Step 3/4/5 as needed. | – Auto-refresh on page load. – Color-coded: Green (>90d), Amber (30-90d), Red (<30d / expired). – Click any tile to drill down. | RC Master data | Dashboard view | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC | No
2 | Receive automated expiry alerts | System sends alerts for expiring RCs at configurable intervals: • 90 days before expiry • 60 days before • 30 days before • On expiry date Process moves to Step 3 (amendment) or Step 4 (renewal) based on action needed. | – Email + in-app notification to TGMSIDC User and GM. – Alert includes: RC ref, equipment, vendor, expiry date, POs issued under this RC. | RC expiry dates | Alert notifications | E-tool | System (auto) | TGMSIDC User | TGMSIDC GM Equip | SO Equipment-TGMSIDC | No | Alert thresholds configurable by admin.
3 | Initiate RC amendment | For changes to an active RC: 1. Select RC to amend 2. Select amendment type (Rate revision / Extension / Scope change / Vendor details) 3. Enter revised details 4. Upload supporting documents 5. Submit for approval Process moves to approval (same workflow as Sheet 3, Step 9). | – Amendment history maintained; original values preserved. – Amendment ref. auto-generated: <RC Ref>-AMD-<serial>. – Same approval workflow as new RC creation. | Active RC; Amendment justification | Amendment request in approval queue | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | ED-TGMSIDC / Vendor | No
4 | Initiate RC renewal process | For expired / expiring RCs: 1. Evaluate renewal need (check pending indents) 2. If renewal needed → initiate new tender 3. Create new RC via Sheet 3, Step 1 – link to predecessor RC Process moves to → Sheet 3. RC Creation (Step 1) if renewal initiated. Process moves to Step 5 if closure decided. | – System flags indents waiting on expired RC. – If no renewal, pending indents re-routed to open tender path. | Expiring RC; Demand data | New RC (via Sheet 3) or closure decision | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | TGMSIDC SO Equip | Yes | If RC not renewed, all indents depending on it get flagged and rerouted.
5 | Deactivate / Close RC | Close an RC when: • Expired and not renewed • Superseded by new RC • Cancelled by authority Process ends for this RC. | – Status = 'Closed' or 'Expired'. – Existing POs under this RC remain unaffected. – No new POs can reference this RC. – Closure reason mandatory. | Closure decision; Reason | Closed RC; Updated master | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Vendors & TGMSIDC SO Equip | No

## 5. Issue PO
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Initiate PO generation | Click 'Generate PO' from the PO module. Process moves to Step 2. | – Auto-generate draft PO number: PO-<FY>-<serial>. – PO creation form opens. | — | Draft PO shell | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
2 | Select financial year | Select the FY during which the PO is being issued. Process moves to Step 3. | – Default = current FY. – Validate FY is active. | — | FY selected | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
3 | Select PO type | Select PO type: RC-based / Local Purchase. Process moves to Step 4. | – PO type drives subsequent field requirements and validations. | — | PO type set | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
4 | Link to approved indent | Select the indent reference number (search option available). Only 'Approved' indents with un-ordered quantities shown. Process moves to Step 5. | – Filter: Status = 'Approved', remaining qty > 0. – Auto-populate indent header details. – Show equipment lines pending PO. | Approved indent list | Indent linked to PO | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
5 | Select equipment from indent | Select equipment line item(s) from the indent for which this PO is being raised. Enter the qty to issue the PO Process moves to Step 6. | – Show only items not fully covered by existing POs. – Display remaining un-ordered quantity. | Indent equipment lines | Equipment lines added to PO | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
6 | Select PO date | Select the date on which the PO is to be issued. Process moves to Step 7. | – Default = today (Can't be modified) | — | PO date set | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
7 | Verify auto-filled RC details | System auto-fills RC details for selected equipment. Review: • L1, L2, L3 bidder details & rates • RC validity period • Supply & installation period Process moves to Step 8. | – Auto-populate from active RC. – Highlight if RC validity < 30 days remaining. – If RC expired → block PO and alert. – Show RC ref. no., vendor details, unit rate. | Active RC data | RC details displayed for review | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | Yes | If RC expired or incorrect, PO cannot proceed until RC is corrected / renewed.
8 | RC details correct? | Decision: • Correct → Process moves to Step 10. • Incorrect → Process moves to Step 9 to modify. | — | — | — | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | — | Yes
9 | Modify RC details (if needed) | Modify incorrect RC linkage or details in RC master Requires supervisor authorization. Process moves back to Step 7 for re-verification. | – Changes logged in audit trail. – Supervisor override required. – After modification → return to Step 7. | RC correction data | Corrected RC linkage | E-tool | TGMSIDC User | TGMSIDC GM Equip | — | — | No
10 | Allocate quantity to vendors | Split order quantity across eligible vendors (L1, L2, L3) per RC terms. Save draft. Process moves to Step 11. | – Validate: Σ vendor allocations = approved indent qty. – Auto-calculate cost per vendor. – Multiple POs generated if >1 vendor allocated. | RC vendor allocation rules | Vendor-wise quantity split | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No | One PO per vendor per equipment type.
11 | Enter consignee details | Map quantities to consignees (institutions). Select institution and assign quantity per consignee. Process moves to Step 12. | – Validate: Σ consignee qty = vendor allocated qty. – Auto-populate institution address from master. – Allow district-wise grouping. | Institution Master; Indent mapping | Consignee delivery schedule | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
12 | Review purchase cost details | Auto-populated: A. Rate/unit (excl. tax) B. GST amount C. Rate/unit (incl. tax) = A + B D. Ordered quantity E. Total equipment cost = A × D F. Net PO cost = C × D Manual entry: G. File no. / Wing / BME H. Generated by I. Remarks Process moves to Step 13. | – All cost fields auto-calculated. – Validate against budget availability (fund deposited − existing PO commitments). – Flag if PO cost exceeds available funds. | RC rates; Indent qty; Fund data | Cost summary; Budget check result | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
13 | Performance Security required? | Decision: • If PS required → Process moves to Step 14. • If PS not required → Process moves to Step 15. | – Default PS requirement based on PO value threshold (configurable). – PS toggle checkbox. | PO value; PS threshold config | PS decision | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | — | Yes
14 | Enter PS percentage | Enter Performance Security % for the PO. Process moves to Step 15. | – Auto-calculate PS amount = Net PO cost × PS%. – Validate PS% within allowed range (e.g., 3-10%). | PS % | PS amount calculated | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | — | No
15 | Edit PO format, T&C, and annexures | Review and edit: • PO format / cover letter • Terms & Conditions • Annexure I (equipment specs) • Annexure II (consignee list) • Annexure III (delivery schedule) Process moves to Step 16. | – Templates pre-loaded from T&C Master based on PO type. – Allow clause-level editing. – Version control on T&C changes. – Standard boilerplate locked; only variable fields editable. | T&C Master templates | Customized PO document | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No
16 | Submit PO for approval | Submit completed PO. Process moves to → Sheet 6. PO Approval (Step 1). | – Status: 'Pending PO Approval'. – Notification to GM Equipment. – PO locked from editing. – Submission timestamp recorded. | Complete draft PO | PO in approval queue; notification | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Respective HoD | No

## 6. PO Approval
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes
1 | Open PO approval queue | Select 'New' POs from PO Status dropdown. Process moves to Step 2. | – Dashboard: pending POs with value, vendor, age. – Sort by value / date / urgency. – Aging: Green <3d, Amber 3-5d, Red >5d. | Pending PO list | Filtered PO list | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
2 | Select PO for review | Enter or select the PO number to open full details. Process moves to Step 3. | – Display: PO header, line items, consignees, cost summary, T&C, annexures. – Comparison view: PO vs. Indent vs. RC (side-by-side). | PO number | Full PO detail view | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
3 | Verify PO details | Verify: • Equipment specs & quantities • RC linkage and rate accuracy • Consignee mapping • Cost calculations & budget • T&C, annexures, PS details Process moves to Step 4. | – System highlights anomalies: rate mismatch, budget overrun, missing fields. – Show indent approval comments for context. | PO data; Indent; RC | Verification outcome | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
4 | Decision: Proposed to Approve / Modify / Reject | • Correct → PO proposed to Approve. • Needs edits → Proposed to Return for Modification. • Fundamentally flawed → Proposed to Reject. Process moves to Step 5. | — | — | — | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | TGMSIDC SO Equipment | Yes
5 | Decision: Approve / Modify / Reject | • Correct → Approve. Process moves to Step 6. • Needs edits → Return for Modification. Process moves to Step 7. • Fundamentally flawed → Reject. Process moves to Step 8. | — | — | — | E-tool | TGMSIDC SO Equipment | TGMSIDC SO Equipment | TGMSIDC GM Equip | Respective HoD/TGMSIDC user
6 | Approve PO | Approve the PO. PO becomes active. Process moves to Step 9. | – Status: 'Approved / Active'. – PO PDF auto-generated. – Notification to vendor, consignees, HoD. – Delivery timeline initiated based on RC supply period. | Approval decision | Active PO; PDF generated; Notifications | E-tool | TGMSIDC SO Equipment | ED-TGMSIDC | TGMSIDC User | HoD / Vendor | No | ED approval required above a PO value threshold configurable by Admin; default set during implementation. Below threshold, SO Equipment is the final approver.
7 | Return PO for modification | Return to PO creator with comments specifying changes. Process moves back to → Sheet 5. Issue PO (Step 1) for corrections. | – Status: 'Returned for Modification'. – Comments mandatory. – Notification to creator. – Modification history tracked. | Return comments | PO back in creator's queue | E-tool | TGMSIDC SO Equipment | TGMSIDC GM Equip | TGMSIDC User | — | No
8 | Reject PO | Reject PO with documented reason. PO is closed. Indent may need fresh PO generation. Process ends for this PO. | – Status: 'Rejected'. – Mandatory rejection reason. – Notification to creator, HoD. – Indent line item qty freed for re-ordering. | Rejection reason | Closed PO; Freed indent qty | E-tool | TGMSIDC SO Equipment | TGMSIDC GM Equip | TGMSIDC User | Respective HoD | No
9 | Vendor receives & acknowledges PO via Vendor Portal | System sends approved PO to vendor electronically. Vendor receives PO notification on Vendor Portal: 1. View full PO details 2. Download PO PDF 3. Acknowledge PO acceptance on portal 4. Enter expected dispatch date 5. Raise queries / clarifications (if any) Process moves to → Sheet 8. Delivery & Receipt (Step 1). | – Auto-email + Vendor Portal notification with PO PDF. – PO appears in vendor's 'New POs' dashboard. – Vendor must acknowledge within 7 calendar days. – Acknowledgement recorded with timestamp. – If no acknowledgement in 7 days → escalation alert. – Expected dispatch date captured for delivery tracking. – Vendor can raise clarification requests via portal. | Approved PO PDF; Vendor Portal notification | Vendor acknowledgement; Expected dispatch date | E-tool | Vendor | TGMSIDC User | TGMSIDC SO Equipment | TGMSIDC User / Consignee | No | Vendor must acknowledge within 7 days. If clarification raised, PO status → 'Clarification Pending'.

## 7. PO Amendment & Cancel
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Identify amendment / cancellation need | Reasons may include: • Quantity change (increase / decrease) • Consignee change • Delivery date extension • Full cancellation Process moves to Step 2. | – System shows amendment options based on PO status. – Block amendments for fully delivered / closed POs. – Amendment allowed only for 'Active' / 'Partially Delivered' POs. | PO data; Amendment justification | Amendment type identified | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendor / HoD | No
2 | Create amendment request | Select PO to amend. Enter: 1. Amendment type 2. Revised details (e.g., new qty, new date) 3. Justification / reason 4. Upload supporting documents Process moves to Step 3. | – Auto-generate amendment ref: <PO No.>-AMD-<serial>. – Original PO values preserved in history. – Amendment linked to parent PO. | Amendment details; Supporting docs | Amendment request | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendor / HoD | No
3 | Submit amendment for approval | Submit to SO Equipment for review. Process moves to Step 4. | – Status: 'Amendment Pending Approval'. – Notification to approver. | Amendment request | Amendment in approval queue | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC SO Equip | — | No
4 | Approve / Reject amendment | SO Equipment reviews and decides. • Approve → PO updated with amended values; revised PO PDF sent to vendor. Process ends (PO updated). • Reject → original PO continues unchanged. Process ends (no change). | – If approved: PO version incremented (v2, v3…). – Revised PO PDF auto-generated. – Vendor & consignee notified. – If rejected: reason logged. | Amendment request; Reviewer's assessment | Updated PO (if approved) / Unchanged PO | E-tool | TGMSIDC GM Equip | ED-TGMSIDC | TGMSIDC User | Vendor / HoD | Yes | Financial amendments above value threshold need ED approval.
5 | PO Cancellation (if applicable) | For full cancellation: 1. Enter cancellation reason (mandatory) 2. Upload supporting document 3. Submit for approval 4. On approval → PO status = 'Cancelled' Process ends for this PO. | – Status: 'Cancelled'. – Indent qty freed for re-ordering. – Vendor notified. – Audit trail of cancellation. – If partial delivery already received, cancel only remaining qty. | Cancellation justification; Supporting doc | Cancelled PO; Freed indent qty; Vendor notification | E-tool | TGMSIDC GM Equip | ED-TGMSIDC | TGMSIDC User | Vendor / HoD | Yes | Cancellation post partial delivery requires reconciliation of received vs. cancelled qty.

## 8. Delivery & Receipt
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Monitor delivery schedule | Track expected deliveries: • POs with upcoming delivery due dates • Overdue deliveries • Deliveries completed today Process moves to Step 2 when vendor intimates delivery. | – Dashboard: due this week / month / overdue. – Auto-reminders to vendor at T-7, T-3, T-1 days. – Overdue alerts to TGMSIDC team. | PO delivery dates | Delivery tracking dashboard | E-tool | TGMSIDC User | TGMSIDC User | TGMSIDC GM Equip | Vendor / Consignee | No
2 | Record vendor delivery intimation | Vendor notifies upcoming delivery via vendor portal Enter: 1. PO reference number 2. Expected delivery date 3. Delivery challan / invoice number 4. Transporter details Process moves to Step 3. | – Link delivery to PO. – Auto-generate Delivery Tracking ID. – Notify consignee of expected arrival. | Vendor intimation | Delivery record; Consignee notification | E-tool | Vendor | Vendor | Vendor | TGMSIDC User | No
3 | Vendor confirms equipment dispatch | Vendor confirms dispatch via Vendor Portal. Enter: 1. PO reference number 2. Dispatch date 3. Expected delivery date at consignee 4. Transporter details (name, vehicle no., LR/GR no.) 5. Invoice / Delivery challan number 6. Dispatch quantity & item details Process moves to Step 4. | – Vendor updates dispatch status on Portal. – Auto-generate Dispatch Tracking ID. – Auto-notification to Consignee & TGMSIDC User. – Status: 'Dispatched – In Transit'. | PO reference; Dispatch details | Dispatch record; Notifications | E-tool | Vendor | Vendor | TGMSIDC User | Consignee / TGMSIDC User | No | If vendor fails to update dispatch within 2 days, system flags 'Dispatch Unreported'.
4 | Receive equipment at consignee site | Consignee receives physical delivery. Perform immediate checks: 1. Compare delivery against challan 2. Count quantity received 3. Visual inspection for transit damage Process moves to Step 5. | – Consignee logs receipt in system (or TGMSIDC User on behalf). – Upload: delivery challan photo, unboxing photos. – Receipt timestamp auto-recorded. | Physical delivery; Challan | Receipt entry in system | E-tool | Consignee | Consignee | TGMSIDC User | TGMSIDC GM Equip | No | If consignee lacks system access, TGMSIDC User enters on their behalf.
5 | Record detailed receipt information | Enter: 1. Actual delivery date 2. Quantity received 3. Equipment serial numbers (per unit) 4. Condition: Good / Damaged / Shortage 5. Upload photos of received equipment Process moves to Step 6. | – Validate: Qty received ≤ PO ordered qty. – Auto-calculate: On-time or Late. – Auto-calculate delay in days if late. | Physical inspection; Serial nos. | Delivery receipt record | E-tool | Consignee | TGMSIDC User | TGMSIDC GM Equip | Vendor | No
6 | Delivery matches PO specifications? | System auto-compares receipt vs. PO: • Correct equipment model & specs? • Correct quantity? • No damage? → Yes: Process moves to Step 8 (Delivery Certificate). → No: Process moves to Step 7 (Log discrepancy). | – Auto-comparison: Receipt vs. PO line items. – Highlight mismatches in red. | Receipt data; PO data | Match / Mismatch result | E-tool | Consignee | TGMSIDC User | TGMSIDC GM Equip | Vendor / Consignee | Yes
7 | Log delivery discrepancy | Record discrepancy: 1. Type: Short delivery / Wrong item / Damaged 2. Detailed description 3. Photographic evidence (mandatory) 4. Action required: Re-delivery / Replacement After resolution → Process moves to Step 8. | – Discrepancy notification auto-sent to vendor. – Block payment for discrepant items. – Escalation if unresolved in 15 days. – Discrepancy linked to vendor performance score. | Discrepancy details; Photos | Discrepancy record; Vendor notification | E-tool | TGMSIDC User | TGMSIDC GM Equip | Vendor | HoD / Consignee | No | Vendor response SLA: 7 working days. Auto-escalation at Day 8.
8 | Vendor obtains Delivery Completion Certificate from Institute | After successful delivery (or discrepancy resolution), vendor obtains a Delivery Completion Certificate from the consignee institute. Certificate includes: 1. PO reference number 2. Equipment details (model, serial nos., quantity) 3. Date of delivery 4. Condition of equipment 5. Authorized signatory & Institute stamp Process moves to Step 9. | – System prompts vendor to collect certificate. – Certificate template available on Vendor Portal. – Status: 'Awaiting Delivery Certificate'. – Auto-reminder at Day 3, Day 5 if not uploaded. | Satisfactory delivery; Institute authorization | Signed Delivery Completion Certificate | E-tool | Vendor | Vendor | Consignee (Institute) | TGMSIDC User | No | Institute must issue certificate within 3 working days. Vendor can raise grievance if delayed.
9 | Vendor uploads Delivery Completion Certificate via Vendor Portal | Vendor uploads signed certificate through Vendor Portal. 1. Scanned copy (PDF/Image) 2. PO reference (auto-populated) 3. Delivery Tracking ID (auto-populated) 4. Date of certificate issuance 5. Remarks (if any) Process moves to Step 10. | – Upload: PDF/JPG/PNG, max 30 MB. – Validate: PO ref & Delivery Tracking ID match. – Certificate linked to PO, Delivery & Receipt records. – Status: 'Delivery Certificate Uploaded'. – Auto-notification to TGMSIDC User with certificate preview. | Signed certificate (scan); PO reference | Certificate record; TGMSIDC notification | E-tool | Vendor | Vendor | TGMSIDC User | TGMSIDC User / GM Equip | No | Vendor must upload within 7 working days. If not, system blocks further processing and escalates.
10 | Route to QA & Acceptance | After Delivery Certificate is uploaded and verified, move to QA. Process moves to → Sheet 9. QA & Acceptance (Step 1). | – Status: 'Pending QA Inspection'. – Notification to QA committee / technical team. – QA inspection due date = receipt date + 7 working days. – Delivery Certificate must be uploaded before QA routing. | Receipt record; Uploaded certificate | QA task created | E-tool | System (auto) | TGMSIDC User | TGMSIDC GM Equip | Consignee / QA team | No

## 9. QA & Acceptance
Step | Activity | Detailed Description | System Behaviour / Validation | Input(s) | Output(s) | Tool | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Decision Point? | Exception Handling / Notes | Link to Overview Sheet
1 | Assign QA / inspection committee | Assign inspection committee: • Technical expert (domain specialist) • End-user representative (from consignee institution) • TGMSIDC representative Process moves to Step 2. | – Committee assignment notification. – Inspection due date = receipt date + 7 working days. – Composition may vary by equipment value / type. | Receipt record; Equipment type | Committee assigned; Inspection scheduled | E-tool | TGMSIDC GM Equip | TGMSIDC GM Equip | TGMSIDC User | Consignee / Committee | No
2 | Conduct physical inspection | Committee inspects: 1. Physical condition & completeness 2. Specification compliance (vs. PO / RC specs) 3. Accessories & documentation present 4. Installation readiness Process moves to Step 3. | – Auto-generate inspection checklist from PO specs. – Record finding per parameter (Pass / Fail / NA). – Upload inspection photos. | Equipment; PO specs; Checklist | Inspection findings per parameter | E-tool / Physical | QA Committee | TGMSIDC GM Equip | TGMSIDC User | Consignee / Vendor | No
3 | Conduct functional / performance testing | Test equipment: 1. Power-on & basic operation 2. Performance against declared specs 3. Safety checks 4. Calibration verification (if applicable) 5. Demo / test run Process moves to Step 4. | – Record test results per parameter. – Upload test certificates / calibration reports. – Note deviations from expected specs. | Equipment; Test protocol | Test results; Certificates uploaded | E-tool / Physical | QA Committee | TGMSIDC GM Equip | TGMSIDC User | Consignee / Vendor | No | Vendor technical support may be required during testing.
4 | Record QA findings & score | Enter consolidated results: 1. Overall status: Pass / Fail / Conditional 2. Parameter-wise Pass/Fail 3. Observations & remarks 4. Upload signed inspection report Process moves to Step 5. | – Auto-score: % parameters passed. – Generate inspection certificate (draft). – All committee members must sign off. | Inspection & test findings | QA report; Draft certificate | E-tool | QA Committee | TGMSIDC GM Equip | TGMSIDC User | Consignee / Vendor | No
5 | Decision: Accept / Conditional / Reject | • Accept → Process moves to Step 6. • Conditional → Process moves to Step 7. • Reject → Process moves to Step 8. | — | — | — | QA Committee | TGMSIDC GM Equip | TGMSIDC User | Consignee / Vendor / HoD | Yes
6 | Accept equipment | Issue acceptance certificate. Triggers: • Equipment installed & added to institution inventory register • Warranty period starts • Payment processing initiated • Installation scheduling (if applicable) If installation required → Process moves to Step 9. If no installation → Process ends (equipment in service). | – Status: 'Accepted'. – Auto-generate acceptance certificate (PDF). – Update equipment inventory register. – Notify Accounts for payment release. – Warranty start date: for equipment NOT requiring installation = acceptance date; for equipment requiring installation = final acceptance (post-installation) date (see Step 9). – TGMSIDC User / Accounts marks PO Payment Status = Paid / Not Paid (manual toggle). This is the only payment data captured in the system; actual disbursement is handled outside the system (PFMS / Treasury). | QA approval | Acceptance certificate; Inventory updated; Payment trigger | E-tool | TGMSIDC GM Equip | ED-TGMSIDC | TGMSIDC User | Consignee / Vendor / Accounts | No | Payment Status is a manual Paid/Not-Paid flag only; payment processing/disbursement is out of system scope.
7 | Conditional acceptance – vendor rectification | Notify vendor of deficiencies. Vendor must rectify / replace within defined timeline. After rectification → Process moves back to Step 2 (re-inspection). | – Deficiency notice auto-generated and sent to vendor. – Rectification SLA: 15 working days. – Auto-escalation if SLA breached. | Deficiency list | Vendor notification; Rectification tracked | E-tool | TGMSIDC User | TGMSIDC GM Equip | Vendor | Consignee / HoD | No | If vendor fails to rectify within 30 days, escalate to LD / cancellation.
8 | Reject equipment | Issue rejection notice with documented reasons. Vendor to collect rejected equipment. Triggers: • Replacement delivery required • Vendor performance debit • LD computation if repeated failure Process moves back to → Sheet 8. Delivery & Receipt (Step 1) for replacement delivery tracking. | – Status: 'Rejected'. – Rejection notice to vendor (auto-email). – PO remains open for replacement. – Vendor performance score updated (penalty). | Rejection decision; Reasons | Rejection notice; PO open for replacement; Vendor score updated | E-tool | TGMSIDC GM Equip | ED-TGMSIDC | TGMSIDC User | Consignee / Vendor / HoD | No | If vendor fails to replace within 30 days → initiate LD / PO cancellation.
9 | Installation & training (if applicable) | For equipment requiring installation: 1. Schedule installation with vendor 2. Record installation date & sign-off 3. Conduct user training 4. Obtain training attendance & sign-off 5. Final acceptance post-installation Process ends (equipment in service). | – Installation status tracked (Pending / Scheduled / Complete). – Training attendance list uploaded. – Final acceptance certificate post installation. – Warranty start date = final acceptance (post-installation) date for equipment requiring installation. | Vendor installation plan; Equipment | Installation complete; Training done; Final acceptance | E-tool / Physical | Vendor | TGMSIDC User | Consignee / TGMSIDC GM Equip | HoD | No | Installation period as per RC supply & installation terms.

## 10. Workflow Summary
A. END-TO-END PROCESS FLOW |  |  |  | Link to Overview Sheet
DEO (HoD) enters indent → TGMSIDC User reviews/verifies against scanned copy & corrects → SO Equipment approves → [RC Creation if no RC] → Issue PO → PO Approval → Delivery & Receipt → QA & Acceptance
B. STATUS TRANSITIONS PER STAGE
Stage | Possible Statuses | Status Trigger | Next Stage
Indent | Draft (DEO) → Pending TGMSIDC Review → Returned by TGMSIDC (to DEO) → Pending Approval (SO queue) → Approved / Returned / Rejected | DEO submits → TGMSIDC reviews/edits/forwards → SO Equipment approves/returns/rejects | If Approved → RC check / PO If Returned by SO → TGMSIDC User (who may return to DEO) If Returned by TGMSIDC → DEO re-edits and re-submits If Rejected → Closed
Rate Contract | Draft → Specs Confirmation (Accepted/Changed/New) → Specs Finalized → Tender Active → Tender Opened → Pre-bid Queries → Amendments → Responses Check → Bid Evaluation → Demo & Tech Eval → Technical Committee (Approved/Not Approved) → Financial Bid & BFC Prep → BFC Stage → BFC Approved/Rejected → Pending RC Approval → Active / Returned / Rejected / Expired / Closed At any tender stage: May be 'Cancelled' (with stage + reason recorded) | Specs: Doctor confirmation → Tender: Stage progression on e-Procurement/GeM → BFC: Committee decision → RC: User action + date-based expiry | If BFC Approved → RC header entry → RC approval → Active (available for PO) If Tender Cancelled at any stage → Re-tender with new reference If RC Expired → RC Management (renew)
Purchase Order | Draft → Pending PO Approval → Active → Dispatched to Vendor → Vendor Acknowledged → Dispatched (In Transit) → Partially Delivered → Fully Delivered → Closed | User action + vendor portal acknowledgement + delivery events | If Active → Dispatch to vendor Delivery events update status
PO Amendment | Draft → Pending Amend. Approval → Approved / Rejected | User action | If Approved → PO updated If Rejected → No change
Delivery | Expected → Intimated → Dispatched (In Transit) → Received → Awaiting Delivery Certificate → Certificate Uploaded → Pending QA → Discrepancy Logged | Vendor portal actions (dispatch, certificate upload) + consignee receipt | If Received (OK) → QA If Discrepancy → Resolution flow
QA & Acceptance | Pending Inspection → Inspected → Accepted / Conditional / Rejected | QA committee decision | If Accepted → Inventory + Payment If Conditional → Vendor rectification If Rejected → Replacement
C. SLA TARGETS
Process Step | SLA Target | Escalation Level 1 | Escalation Level 2
Indent data entry finalisation | 2 working days | GM Equipment – Day 3 | SO Equipment – Day 5
Indent approval | 3 working days | ED – Day 4 | MD – Day 7
RC creation (post tender finalization) | 3 working days | GM Equipment – Day 4 | ED – Day 7
RC approval | 3 working days | ED – Day 4 | MD – Day 7
PO generation | 3 working days from indent approval | GM Equipment – Day 4 | ED – Day 7
PO approval | 2 working days | ED – Day 3 | MD – Day 5
Vendor PO acknowledgement | 7 calendar days from PO issue | TGMSIDC User – Day 8 | GM Equipment – Day 10
Vendor delivery | As per RC supply period | GM Equipment – Day +7 | LD initiation – Day +15
Vendor dispatch intimation (via portal) | 2 working days from actual dispatch | TGMSIDC User – Day 3 | GM Equipment – Day 5
Delivery certificate upload (via portal) | 7 working days from delivery | TGMSIDC User – Day 8 | GM Equipment – Day 10; Block PO processing
QA inspection | 7 working days from receipt | GM Equipment – Day 8 | SO Equipment – Day 14
Vendor rectification | 15 working days from notice | GM Equipment – Day 16 | PO cancellation review – Day 30
D. PARALLEL PROCESSING RULES
Scenario | Parallel Path Allowed | Condition
Single indent with multiple equipment types | Each equipment type routed independently (some to RC, some to PO, some to tender) | Indent approved with mixed procurement modes
Single equipment, multiple vendors (L1/L2/L3) | Separate POs generated per vendor in parallel | RC allocation across vendors
Multiple consignees on single PO | Deliveries tracked independently per consignee site | PO dispatched with multi-consignee schedule
Multiple RCs being created simultaneously | Independent RC creation processes run in parallel | Multiple tenders concluded for different equipment
QA for multiple deliveries | Independent QA committees can inspect simultaneously | Equipment delivered to different consignees

## 11. Master Data
MASTER DATA REQUIREMENTS | [5 empty] | Link to Overview Sheet
# | Master List | Key Fields | Maintained By | Update Frequency | Used In Modules
1 | Equipment Master | Equipment ID, Name, Facility Type (Medical College / Hospital / PHC etc.), Category, Department, HSN Code, Specifications Template, Cost/unit, Active (Y/N) | TGMSIDC Admin | As needed (GM approval for additions) | Indent, RC, PO, QA
2 | Institution Master | Institution ID, Name, Facility Type (Medical College / Hospital / PHC etc.), District, Full Address, Contact Person, Phone, Email | TGMSIDC Admin | Annually / As needed | Indent, PO (consignee), Delivery
3 | Vendor Master | Vendor ID, Company Name, GSTIN, PAN, Registered Address, Contact Person, Phone, Email, Bank Details, Performance Score, Portal Login ID, Portal Status (Active/Inactive), Last Login Date, Notification Preferences (Email/Portal/Both) | TGMSIDC Admin | As needed (post tender) | RC, PO, Delivery, QA, Vendor Portal
4 | Account Head Master | Account Head ID, Name, Description, Budget Code, Active (Y/N) | TGMSIDC Admin | Annually | Indent
5 | Programme Master | Programme ID, Name, Funding Source (linked), Validity Period, Budget Allocation | TGMSIDC Admin | Annually | Indent
6 | Funding Source Master | Source ID, Name, Type (State / Central / Externally Aided), Description | TGMSIDC Admin | As needed | Indent (via Programme)
7 | Indent Type Master | Type ID, Name (Letter, GO, Proceeding, etc.), Description | TGMSIDC Admin | Rarely | Indent
8 | Authority Master | Authority ID, Name, Designation, Department, Contact Details, Approval Level | TGMSIDC Admin | As needed | Indent, Approval workflows
9 | District Master | District ID, District Name, State, Region / Zone | System (static) | Rarely | Institution linkage
10 | Tax / GST Slab Master | Tax Type, GST Slab %, IGST / CGST+SGST rates, HSN range, Effective Date | TGMSIDC Admin | As per govt. notification | RC, PO (cost calculation)
11 | T&C Template Master | Template ID, PO Type, Clause List (editable / locked flags), Version, Effective Date | TGMSIDC Admin | As needed | PO (T&C, Annexures)
12 | User & Role Master | User ID, Full Name, Role (Admin / TGMSIDC User / GM / ED / DEO (HoD) / Consignee / Vendor Portal), HoD Mapping (for DEO role), Module Access, Status (Active / Inactive) | System Admin | As needed | All modules (access control), Vendor Portal, DEO indent entry

## 12. Functionalities
# | Module | Functionality | Detailed Description | Business Rule / Validation | Priority (H/M/L) | Use Case / Benefit
1 | Indent | Account head management | Admin can add/edit/deactivate account heads from master | Names must be unique; deactivation (not deletion) for unused entries | H | Standardize indent categorization; avoid free-text errors
2 | Indent | Equipment master management | Add equipment with name, facility type, category, department, spec template, HSN code | Equipment + department combination must be unique; GM approval for new additions | H | Consistent equipment naming; spec templates speed up data entry
3 | Indent | Programme & funding source management | Maintain programme names linked to funding sources and FY budgets | Programme linked to funding source; budget allocation tracked | H | Track procurement spending by programme
4 | Indent | Indent type management | Maintain indent types (Letter, GO, Proceeding, etc.) | Admin-only; types pre-defined | M | Classify indents for analytics
5 | Indent | Indent register / tracker view | Unified view of all indents with real-time status, filters, search | Filterable by: FY, authority, status, equipment, institution, date range | H | Single pane of glass for indent lifecycle visibility
6 | Indent | Equipment count & PO linkage per indent | Show # equipment types per indent, # POs issued against each, remaining qty | Auto-calculated from PO data | M | Quick indent completeness check
7 | Indent | Duplicate indent detection | System flags potential duplicate: same equipment + institution + FY | Warning shown (not hard block); user can override with justification | H | Prevent double procurement
8 | RC | RC dashboard with expiry tracking | Dashboard: Active / Expiring (30/60/90d) / Expired RCs; filterable | Color-coded expiry indicators; click-through to RC details | H | Proactive RC lifecycle management
9 | RC | Automated expiry alerts | Email + in-app alerts at 90, 60, 30, 0 days before RC expiry | Configurable thresholds per equipment category | H | Prevent procurement delays due to expired RC
10 | RC | RC amendment & renewal tracking | Track amendment history; link old RC → new RC upon renewal | Amendment audit trail; renewal lineage maintained | M | Continuity and audit compliance
11 | RC | Vendor master management | Maintain vendor details, GST/PAN validation, bank info, performance history | GSTIN format validation; PAN cross-check; unique vendor ID | H | Vendor data integrity; avoid duplicate vendors
12 | PO | Auto-populate RC data in PO | When creating PO, auto-fetch rates, vendor details, tax from linked RC | Only active (non-expired) RCs shown | H | Eliminate manual rate entry errors
13 | PO | PO cost auto-calculation | Auto-calculate unit tax, total cost, net PO value from rate × qty | GST computation per Tax Master; budget availability check | H | Accurate, error-free costing
14 | PO | PO amendment & cancellation tracking | Full version history of amendments; cancellation with reason & freed qty | Amendment audit trail; version numbering (v1, v2…) | H | Compliance, audit, and traceability
15 | PO | Multi-vendor PO split from single indent | Split indent equipment qty across L1/L2/L3 vendors per RC allocation | Σ vendor qty = approved indent qty | H | Support RC allocation rules
16 | Delivery | Delivery tracking dashboard | Track expected, overdue, completed deliveries with vendor-wise view | Auto-reminders to vendor (T-7, T-3, T-1); overdue escalation | H | On-time delivery monitoring
17 | Delivery | Receipt & discrepancy logging | Record receipt qty, serial nos., condition; log discrepancies with photos | Qty received ≤ PO qty; photo mandatory for discrepancy | H | Delivery accountability; vendor performance data
18 | QA | Auto-generated inspection checklist | Checklist auto-created from PO equipment specifications | Parameters from equipment specs + standard QA checks | H | Standardized, consistent QA process
19 | QA | Acceptance / rejection certificate generation | Auto-generate acceptance or rejection certificate PDF upon QA decision | Digital signatures (or uploaded signed copy) | M | Formal documentation for payment & warranty
20 | QA | Installation & training tracking | Track installation schedule, completion, user training & sign-off | Installation status: Pending / Scheduled / Complete | M | Ensure full deployment before final acceptance
21 | Vendor Portal | PO notification & acknowledgement | Vendor receives PO notification on portal; views PO details, downloads PDF, acknowledges acceptance, enters expected dispatch date | Acknowledgement within 7 days; escalation if unacknowledged; clarification request workflow | H | Faster PO acceptance cycle; eliminates manual follow-ups; audit trail of vendor acknowledgement
22 | Vendor Portal | Dispatch intimation & tracking | Vendor updates dispatch status: dispatch date, transporter details, challan no., expected delivery date; TGMSIDC User & Consignee auto-notified | Dispatch linked to PO; auto-generate Dispatch Tracking ID; status 'In Transit' | H | Real-time dispatch visibility; proactive delivery tracking; vendor accountability
23 | Vendor Portal | Delivery Completion Certificate upload | Vendor uploads signed Delivery Completion Certificate (PDF/JPG/PNG); system validates PO & Delivery ID match; TGMSIDC User auto-notified with certificate preview | Upload within 7 working days; max 30 MB; certificate linked to PO, delivery & receipt records; blocks QA routing if not uploaded | H | Formal delivery closure; certificate traceability; payment prerequisite documentation
24 | Vendor Portal | Vendor PO dashboard & reports | Vendor self-service dashboard: POs issued, POs acknowledged, POs fulfilled, pending deliveries, overdue POs, delivery timeline, certificate upload status | Vendor sees only own POs; real-time data; filterable by FY, date range, status, equipment | H | Vendor self-service reduces TGMSIDC query load; transparency; performance awareness
25 | Vendor Portal | Vendor performance self-view | Vendor can view own performance score: on-time delivery %, QA first-pass rate, discrepancy count, overall score vs. threshold | Read-only; score calculated by system; vendor cannot modify; shows trend over time | M | Vendor self-improvement; reduces disputes on performance deductions
26 | Vendor Portal | Vendor grievance & clarification module | Vendor can raise queries on PO terms, report institute delays in certificate issuance, request delivery date extensions with justification | Auto-routed to TGMSIDC User; SLA: 3 working days response; escalation to GM if unresolved | M | Structured dispute resolution; audit trail; reduces informal communication
27 | Vendor Portal | Vendor notification centre | Centralized notification inbox: PO issuance, acknowledgement reminders, dispatch reminders, delivery SLA alerts, discrepancy notices, certificate upload reminders, payment status updates | In-app + email notifications; configurable preferences per vendor; read/unread tracking | H | Single pane for all vendor communications; reduces missed notifications; SLA adherence
28 | General | Role-based access control (RBAC) | Roles: Admin, TGMSIDC User, GM Equip, ED, Consignee (limited), Vendor Portal (PO view, acknowledge, dispatch, certificate upload, own reports, grievance) | Permission matrix per module per action (view/create/edit/approve/delete) | H | Data security; separation of duties
29 | General | Comprehensive audit trail | Log every action: user, timestamp, action type, before-value, after-value | Immutable log; viewable by Admin and GM | H | Compliance, accountability, dispute resolution
30 | General | Document upload & management | Upload, store, retrieve documents at each process step | File type (PDF/JPG/PNG), max 30 MB; virus scan; link to process step | H | Document traceability across procurement lifecycle
31 | General | Notification engine (email + in-app) | Status change notifications, approval requests, SLA alerts, expiry reminders For high-urgency events, SMS is also sent (see functionality #45 for the defined SMS event list). | Configurable per role: which notifications to receive | H | Process visibility; SLA adherence; reduced follow-ups
32 | General | Configurable dashboards & analytics | Role-based dashboards with KPI tiles, charts, drill-down capability | Real-time data; configurable date range & facility filters | H | Decision support for GM / ED
33 | General | Export & print capability | Export any list / report to Excel or PDF; print PO / RC / certificates | Standard export formats; print-optimized layouts | H | Offline review; physical record keeping
34 | DEO (HoD) | DEO login & indent entry | DEO at each HoD logs in with HoD-specific credentials and enters indent details directly into the tool. DEO can only create/edit indents for their own HoD. | Role-based access: DEO sees only their HoD's data; HoD name auto-filled from login profile (read-only); cannot access RC, PO, Delivery, QA modules | H | Eliminates physical indent transfer to TGMSIDC; faster data capture at source; reduces manual re-entry errors
35 | DEO (HoD) | Equipment write-in (not in master) | If DEO cannot find equipment in master list, they can select 'Equipment not in list' and type equipment name + specifications as free-text. Entry flagged as 'Unverified – Pending Master Mapping'. | Write-in entries flagged with 'Unverified' badge; system logs 'From Master' vs 'Write-in' per line; TGMSIDC User must resolve before forwarding to GM | H | DEO is never blocked by incomplete master data; captures real-world equipment needs; TGMSIDC User resolves to maintain master integrity
36 | Indent | TGMSIDC review against scanned copy | TGMSIDC User reviews DEO-entered data side-by-side with the uploaded scanned copy of the original indent to verify accuracy. | Side-by-side view: entered data (left) vs. scanned copy (right); discrepancies highlighted; write-in flags shown prominently | H | Verification against source document ensures data integrity; catches DEO entry errors before GM sees the indent
37 | Indent | TGMSIDC User edit with audit trail | TGMSIDC User can edit/correct any DEO-entered field. Every edit tracked: DEO original value, TGMSIDC corrected value, timestamp, user ID. | Immutable edit audit trail per field; edited fields visually marked (blue highlight); correction count per indent aggregated for DEO quality reporting | H | Ensures data accuracy while maintaining full accountability; enables DEO performance tracking and training needs identification
38 | Indent | Equipment write-in resolution workflow | TGMSIDC User resolves each write-in entry: (A) Map to existing master item if DEO used different name, or (B) Raise 'New Equipment Addition Request' to GM for master data update. | Resolution mandatory before forwarding to GM; Option A updates line to master reference (write-in text preserved in notes); Option B creates request auto-routed to GM | H | Prevents master list pollution with duplicates; ensures every equipment line has a validated master reference or formal addition request
39 | Reporting | DEO Data Quality Report (Indent Accuracy) | Report tracking DEO performance: correction rate per DEO, common error types, write-in frequency, average corrections per indent, trend over time. | Filterable by: HoD, DEO, FY, date range; shows correction count, fields corrected, write-in count, DEO accuracy score | M | Identify DEOs needing training; track data quality improvement over time; accountability for HoD data entry quality
40 | RC | Technical specification confirmation workflow | For existing equipment: specs pre-loaded, doctor confirms (Accepted/Changed). For new equipment: specs entered fresh. In both cases: upload signed spec document, enter doctor/approver names, auto-timestamp. | Mandatory upload of signed document; mandatory approver names; date/time auto-filled; spec version history maintained (original vs. changed); audit trail per confirmation | H | Ensures specs are validated by medical experts before tendering; maintains accountability with signed documents
41 | RC | Tender stage tracking (10 stages) | Track tender lifecycle within our tool: Opened → Pre-bid Queries → Amendments → Responses → Bid Evaluation → Demo & Tech Eval → Technical Committee → Financial Bid & BFC Prep → BFC → BFC Decision. Each stage has date fields, document uploads, and status tracking. | Sequential stage progression; each stage has specific fields; status bar shows current stage; all stages linked to single tender reference | H | Complete tender lifecycle visibility within our tool; no need to switch to e-Procurement for status
42 | RC | Tender cancellation with audit trail | At any tender stage (Steps 7-16), user can cancel tender. Must select stage of cancellation and enter mandatory reason. Cancelled tender preserved in audit. Fresh tender linked as re-tender. | Cancellation stage dropdown; mandatory reason; cancelled record never deleted; re-tender linked to predecessor; notification to GM/ED | H | Full transparency on why tenders were cancelled; audit compliance; re-tender traceability
43 | Reporting | Tender Audit Report | For each equipment, track all tenders: Equipment Name ¦ Tender Ref No ¦ Tender Date ¦ Status (Cancelled/Approved) ¦ If Cancelled: Stage + Reason. Shows complete tender history per equipment. | Filterable by: Equipment, FY, Status, Date range; drill-down from equipment to tender detail; shows re-tender linkages | H | Complete audit trail of all tenders per equipment; identifies procurement delays due to cancellations
44 | General | Automated Vendor Performance Scoring | System calculates vendor performance score in real-time based on weighted formula: On-time delivery rate (40%) + QA first-pass acceptance rate (35%) + Contractual compliance (25%). Score recalculated automatically whenever a delivery receipt, QA decision, or PO acknowledgement event is recorded. Scoring period : 12 months | Contractual compliance = weighted average of 3 sub-metrics (equal weight): (a) PO acknowledgement within 7-day SLA, (b) dispatch intimation within 2-day SLA from actual dispatch, (c) delivery certificate upload within 7-day SLA from delivery. Score range: 0–100. Displayed on Vendor Portal (read-only) and in Vendor Performance Report. Score trend tracked over 6-month periods. | H | Objective, data-driven vendor evaluation; reduces manual scoring effort; enables performance-based vendor management and procurement decisions
45 | General | SMS notifications for critical events | SMS alerts sent for high-urgency events in addition to email and in-app notifications. SMS events — To Vendor: (a) New PO issued, (b) Delivery SLA breach (overdue), (c) Delivery certificate upload overdue. To TGMSIDC GM/SO: (d) Vendor PO acknowledgement overdue (Day 8+), (e) QA inspection SLA breach (Day 8+). To Consignee: (f) Vendor dispatch intimation (equipment in transit). | SMS limited to 6 event types to control costs; SMS gateway costs borne by vendor as part of contract; mobile numbers sourced from User & Role Master and Vendor Master; SMS delivery status tracked (sent/delivered/failed); admin can enable/disable SMS per event type | H | Ensures time-critical alerts reach recipients even when email/portal is not checked; reduces delays in PO acknowledgement, delivery, and QA inspection; improves SLA compliance

## 13. Reports & Dashboards
REPORT SPECIFICATIONS | [9 empty] | Link to Overview Sheet
# | Report Name | Req. § | Objective | Key Data Points / Columns | Filters Available | Drill-Down Capability | Export | Refresh | Primary User
1 | Procurement Pipeline Report | 3.2.1 | End-to-end view of all indents across procurement stages | Indent Ref, Equipment, Institution, Current Stage, Days in Stage, Next Action Owner, Procurement Mode | FY, Date range, Authority, Equipment category, Institution / District, Stage, Status | Click indent → full indent journey; Click stage → items at that stage | Excel, PDF | Daily / On-demand | SO/ GM / ED
2 | Indent Aging Report | 3.2.1 | Identify bottlenecks by analyzing how long indents stay at each stage | Indent Ref, Stage, Date Entered Stage, Days in Stage, SLA Target, SLA Status (Met / Breached), Owner | FY, Date range, Stage, SLA status (Met/Breached), Authority, Facility | Click indent → detail; Click stage → aging distribution chart | Excel, PDF | Daily / On-demand | SO/ GM / ED
3 | Vendor Performance Report | 3.2.2 | Evaluate vendors on delivery timeliness, quality, and contractual compliance | Vendor Name, # POs, On-time Deliveries, Late Deliveries, On-time %, QA Pass Rate, Rejection Count, Avg Delay (days), Compliance Score | Vendor, Date range, Equipment category, FY | Click vendor → PO-wise detail; Click equipment → vendor comparison | Excel, PDF | Daily / On-demand | SO/ GM / ED
4 | Equipment Status / Inventory Report | 3.2.3 | Complete inventory of procured equipment with location and lifecycle data | Equipment Name, Serial No., PO Ref, Vendor, Institution, District, Delivery Date, Installation Date, Warranty Expiry, CAMC Status, Current Status (Active / Under Repair / Decommissioned), Equipment Age | Equipment category, Institution, District, Status, Warranty status, Age range, Date range | Click equipment → full procurement history; Click institution → all equipment there | Excel, PDF | Monthly / On-demand | SO/ GM / Consignee
5 | RC Expiry & Renewal Status Report | 3.2.4 | Track RC lifecycle: active, expiring, expired; support renewal planning | RC Ref, Equipment, Vendor(s), Start, End, Days to Expiry, Status (Active / Expiring / Expired), # POs Issued, Total Value, Renewal Action Needed | Status, Equipment, Vendor, Expiry window (30/60/90d), FY | Click RC → full detail + PO history; Click vendor → all RCs with vendor | Excel, PDF | Weekly | SO/ GM / ED
6 | PO Status Tracker | 3.2.1 | Track all POs from creation through delivery and payment | PO No., Indent Ref, Equipment, Vendor, PO Date, PO Value, Delivery Status, QA Status, Payment Status, PO Age | PO status, Vendor, Date range, FY, Equipment, Value range, Consignee | Click PO → full PO detail + delivery timeline; Click vendor → all POs | Excel, PDF | Daily / On-demand | User / GM / SO
7 | Budget Utilisation Report | 3.2.1 | Fund allocation vs. committed vs. spent across programmes and account heads | Programme, Account Head, Fund Sanctioned, Fund Deposited, PO Value (Committed), Payment Released, Balance Available, Utilisation % | FY, Programme, Account Head, Authority, Date range | Click programme → indent-wise breakdown; Click account head → PO detail | Excel, PDF | Monthly | GM / ED / Finance
8 | Delivery Compliance Report | 3.2.2 | Track delivery SLA compliance and discrepancy resolution | PO Ref, Vendor, Expected Date, Actual Date, Delay (days), Discrepancy Type, Resolution Status, Resolution Time | Vendor, Date range, On-time/Late, Discrepancy status | Click PO → delivery detail; Click vendor → delivery trend | Excel, PDF | Weekly | SO/ GM
9 | QA & Acceptance Summary | 3.2.2 | Quality inspection results and acceptance trends | Equipment, Vendor, PO Ref, Inspection Date, Result (Accept/Conditional/Reject), Issues Found, Resolution Status, Resolution Time | Vendor, Equipment, QA result, Date range, Institution | Click entry → inspection report; Click vendor → QA trend chart | Excel, PDF | Monthly | SO/ GM / QA Committee
10 | SLA Compliance Dashboard | 3.2.1 | Process efficiency metrics across all stages | Stage, Total Items, Within SLA, SLA Breached, Compliance %, Avg Processing Time, Max Pending Item, Owner | Stage, Date range, FY, Owner | Click stage → breached items with owner details | Dashboard | Real-time | SO/ GM / ED
11 | Vendor PO Summary Report (Vendor Portal) | 3.2.5 | Vendor self-service view of all POs: issued, acknowledged, dispatched, delivered, fulfilled, pending | PO No., Equipment, PO Date, PO Value, Acknowledgement Date, Dispatch Date, Delivery Date, QA Status, Certificate Status, Payment Status, PO Age, Fulfilment Status | FY, Date range, PO status, Equipment category | Click PO → full PO detail + delivery timeline + certificate status | Excel, PDF | Real-time | Vendor
12 | Vendor Delivery & Certificate Status Report (Vendor Portal) | 3.2.5 | Track all deliveries by vendor: dispatch status, delivery dates, certificate upload status, overdue items | PO Ref, Equipment, Dispatch Date, Expected Delivery, Actual Delivery, On-time/Late, Delay (days), Certificate Uploaded (Y/N), Certificate Date, Upload Deadline, Overdue Flag | Date range, Delivery status, Certificate status, On-time/Late | Click delivery → dispatch details + receipt record + certificate preview | Excel, PDF | Real-time | Vendor
13 | Vendor Performance Self-View Report (Vendor Portal) | 3.2.5 | Vendor's own performance scorecard: on-time delivery %, QA pass rate, discrepancy count, overall score, trend over time | Period, # POs, # Deliveries, On-time %, Late %, Avg Delay (days), QA First-Pass %, Discrepancy Count, Rectification Time (avg), Overall Score, Score Trend (6-month) | FY, Date range, Equipment category | Click metric → PO-wise breakdown; Click period → monthly trend chart | PDF | Monthly | Vendor
14 | DEO Data Quality / Indent Accuracy Report | 3.2.6 | Track data entry quality by DEO: correction rates, error types, write-in frequency, accuracy trends | DEO Name, HoD, # Indents Entered, # Fields Corrected by TGMSIDC, Correction Rate %, Common Error Fields, # Write-in Entries, Write-in Resolution Rate, Accuracy Score, Trend (6-month) | HoD, DEO, FY, Date range | Click DEO → indent-wise correction detail; Click HoD → all DEOs comparison | Excel, PDF | Monthly | TGMSIDC GM / Admin
15 | Tender Audit Report | 3.2.7 | Complete audit trail of all tenders per equipment — tracks tender history including cancellations, re-tenders, and approvals | Equipment Name, Equipment Category, Tender Ref No, Tender Date, Tender Type (Open/Limited/GeM), Current Stage, Status (Active/Cancelled/Approved), If Cancelled: Stage of Cancellation, Reason for Cancellation, Re-tender Ref (if applicable), BFC Approval Date (if approved), RC Ref (if RC created), Total Tender Duration (days) | Equipment, FY, Status (Active/Cancelled/Approved), Tender type, Date range, Portal (e-Procurement/GeM) | Click equipment → all tenders for that equipment (chronological); Click tender → full stage-wise detail with dates and documents; Click cancelled → cancellation reason and stage | Excel, PDF | On-demand / Weekly | TGMSIDC GM / ED
DASHBOARD KPI SPECIFICATIONS
# | KPI Name | Calculation Logic | Target | Display Type | Owner
1 | Avg Indent-to-PO Cycle Time | Mean(PO Approval Date − Indent Receipt Date) | ≤ 15 working days | Gauge + Trend line | SO/ GM / ED
2 | Avg PO-to-Delivery Cycle Time | Mean(Delivery Date − PO Dispatch Date) | ≤ RC supply period | Gauge + Trend line | SO/ GM
3 | Indent Approval Rate | (Approved Indents / Total Submitted) × 100 | ≥ 90% | Percentage tile | SO/ GM / ED
4 | On-time Delivery Rate | (On-time Deliveries / Total Deliveries) × 100 | ≥ 85% | % tile + Vendor bar chart | SO/ GM
5 | QA First-Pass Acceptance Rate | (Accepted on 1st Inspection / Total Inspected) × 100 | ≥ 90% | % tile + Trend | SO/ GM / QA
6 | Active RC Coverage | (Equipment types with Active RC / Total Equipment types) × 100 | ≥ 80% | Percentage tile | SO/ GM / ED
7 | Budget Utilisation Rate | (Committed + Spent / Sanctioned) × 100 | Per programme target | Bar chart by programme | ED / Finance
8 | Pending Actions (by stage) | Count of items pending action, grouped by stage | Minimize | Stage-wise bar chart | SO/ GM / ED
9 | SLA Compliance Rate | (Items within SLA / Total Items) × 100, by stage | ≥ 95% | Stage-wise % bars | SO/ GM / ED
10 | Vendor Performance Score | Weighted: On-time delivery (40%) + QA pass rate (35%) + Contractual compliance (25%) | ≥ 80 / 100 | Vendor scorecard | SO/ GM / ED
11 | Vendor PO Acknowledgement Rate | (POs Acknowledged within SLA / Total POs Dispatched to Vendor) × 100 | ≥ 95% | % tile + Trend line | SO/ GM / Vendor
12 | Delivery Certificate Upload Compliance | (Certificates Uploaded within SLA / Total Completed Deliveries) × 100 | ≥ 90% | % tile + Vendor bar chart | SO/ GM / Vendor